## Questions
S.No | Analysing a Tender Document & Identifying Key Aspects in a Tender Document
1 | Client Name
2 | Funding Agency, if any
3 | Bidding System
4 | Name of the Work
5 | Project Location
6 | Completion Period
7 | Estimated Cost
8 | Cost of Tender Document
9 | Earnest Money Deposit (EMD)
10 | Important Dates
11 | Pre-bid meeting?
12 | Joint Venture?
13 | Power of Attorney
14 | Site Visit?
15 | Geotechnical Investigation Reports
16 | Land Availability
17 | Other land availability
18 | Technical bid submittals
19 | Financial/Cost bid submittals
20 | Bid Validity
21 | Grounds for bid rejection
22 | Eligibility Criteria
23 | Documents to be submitted

## Answers Set-1 (hidden)
S.No | Term | Synonyms / Alternate Phrases | Answer
1 | Client Name | Employer / Project Owner / Principal / Contracting Authority | Bangalore Metro Rail Corporation Ltd. (BMRCL)
2 | Funding Agency, if any | Financier / Sponsor / Donor Agency / Funding Authority | EIB (European Investment Bank) and AIIB (Asian Infrastructure Investment Bank) (Subject to loan approval) - part of the funding with GoI and GoK(equity Split)
3 | Bidding System | Tendering Process / Bid Submission Format | Single stage – Two Envelope System (Technical & Financial separately) Envelope-1: Tender Security. (Details in NIT and ITT Clause 13) Envelope-2: Technical Proposal. (Details in ITT Clause 9.2) Envelope-3: Financial Proposal. (Details in ITT Clause 9.4) Envelope-4: Outer Envelope.
4 | Name of the Work | Project Title / Scope of Work / Work Description / Contract Name | Design & Construction of Underground Structures (Tunnels & Stations) from Shivajinagar (Excl.) to Tannery Road (Excl.), 2.884 km, including Cantonment and Pottery Town UG stations, Reach-6, Phase-2
5 | Project Location | Site Address / Worksite / Construction Site / Project Area | Bangalore, Karnataka, India; Reach-6 Metro - Shivajinagar to Tannery Road
6 | Completion Period | Duration / Timeframe / Contract Period / Execution Time | 42 Months (1260 days) from date of signing Contract Agreement
7 | Estimated Cost | Project Value / Budget Estimate / Approximate Cost / Cost Projection | ₹ 1105.42 Crores
8 | Cost of Tender Document | Tender Fee / Bid Document Charges / Application Fee / Document Cost | ₹ 56,000 (inclusive of GST)
9 | Earnest Money Deposit (EMD) | Bid Security / Tender Deposit / Performance Guarantee (initial) | ₹ 11.06 Crores (in form of BG/Pay Order/DD, valid for 240 days from date of bid submission)
10 | Important Dates |  | - Issue: 26.06.2018
- Sale up to: 07.08.2018
- Pre-bid meeting: 16.07.2018
- Last date of queries: 17.07.2018
- Submission: 07.09.2018 (11:00–15:00 Hrs)
- Opening: 07.09.2018 (15:30 Hrs)
11 | Pre-bid meeting? | Pre-tender Conference / Clarification Meeting / Bidder's Meeting | Yes; 16/07/2018 at 11:00 am
12 | Joint Venture? | Consortium / Partnership / JV Agreement / Strategic Alliance | Allowed; max 3 partners, with rules on % participation (Lead ≥ 50%, Others ≥ 25%)
13 | Power of Attorney | Letter of Authorization / POA / Authority Letter / Legal Mandate | Required, both for signing the bid and for JV arrangements; foreign PoAs to be notarized and legalized
14 | Site Visit? | Site Inspection / Pre-bid Visit / Field Visit / On-site Evaluation | Mandatory, at own cost/risk; was advised by employer for all bidders, given data is for guidance only.
15 | Geotechnical Investigation Reports | Soil Investigation Report / Geo Report / Subsurface Study / Soil Testing Report | Reference data provided; tenderers can carry out their own investigation for bid preparation
16 | Land Availability | Site Access / Land Ownership / Plot Readiness / Site Handing-over | The notification for land acquisition has been issued and is in process. The joint measurement work is under process and the final notification is awaited. The Tender for demolition of buildings is invited and awarded. Casting yard land (near Peenya Depot ~23,261 sqm) provided for casting activities; more land, if required, must be arranged by contractor, Necessary permanent utility diversion to done by the employer thorugh the separate contract.
17 | Other land availability | Right of Way (RoW) / Utility Relocation Status / Encumbrance Clearance | No additional land acquisition support from employer beyond specified casting yard
18 | Technical bid submittals | Qualification Documents / Tech Proposal / Technical Documents | - Technical Proposal Vol-1, 2, 3 (duly signed, stamped)
- Annual & Financial Reports
- Memorandum & Article of Association
- Addenda/Corrigenda
- All eligibility/qualifying documents, power(s) of attorney, MoU/JVA if JV
- Approach & Methodology, Site Organization, Work Programme, Equipment, Key Personnel, Safety/Quality Plans, Statement of Deviations [see section 9.2, 9.2.1, 9.2.2, EQC]
19 | Financial/Cost bid submittals | Price Proposal / Commercial Bid / Cost Sheets / BOQ Submission | - Financial Proposal in separate sealed envelope
- Summary of Price Bid
- Form of Price Bid
- Preamble
- Schedule-C BOQ & Breakup of Payment
- Appendix-35 (Pricing of Conditions/Deviations)
20 | Bid Validity | Proposal Validity / Offer Duration / Tender Validity Period | 180 days from date of submission
21 | Grounds for bid rejection | Disqualification Reasons / Non-compliance Issues / Rejection Criteria | - Late bid
- Non-submission/invalid EMD
- No separate sealed envelopes for Tech/Fin
- Not meeting eligibility/qualification
One institute One bid
- Conflict of interest/prohibited, fraudulent, or corrupt practices
- False information, errors, insufficient documentation, modification attempts after deadline, etc. [Detailed in ITT 2.7, 13.2, 21, and EQC]
22 | Eligibility Criteria | Prequalification Requirements / Qualification Norms / Bidder Criteria | - Work experience: Similar nature (TBM tunnel, min. 5m dia.), ≥3.92 km in last 10 years (JVs allowed conditions apply)
Bid capacity should be greater than or equal to the cost of the current project.
- DDC: Work for at least 2 UG metro stations & 1.0 km tunnel
- Financial: Positive net worth last 2 FYs, EBIT positive 2 out of last 5 FYs, liquidity ≥₹221.08 Cr, annual turnover min. ₹947.50 Cr for 2 years out of last 5, bid capacity ≥₹1105.42 Cr (See detailed EQC Sec-C, pages 3-9)
23 | Documents to be submitted | Credentials to be submitted/Submittals/Contractual deliverables | - All as per ITT 9.2/9.4 and EQC 1.3/1.5/2.3/3.4 etc.
- Forms of Tender, Appendices 8–17, 28, 31–35, technical/financial forms, DDC warranty, Key personnel CVs, plant/machinery list, etc.

## Sheet1 (hidden)
To | From
1 | 4 | Cover Page
5 | 5 | Tender notification | Section A
6 | 8 | NIT
9 |  | Index of - Instructions to tenders (ITT) | Section B - (divided into Section-A-F)
10 | 24 | Details of ITT
25 | 25 | Drawing - Area of casting yard
26 | 26 | Index-of EQC | Section C
27 | 34 | Details of EQC
35 | 36 | Index of form of tender | Section D
37 | 91 | Details of form of tender

## Approaches (hidden)
Dtae
1 | Iteration -1 | Holistic ideas of 23 key aspects | 14.09.2025
|  | Meeting with Professor and suggestions | 15.09.2025
| Iteration -2 | Detailed analysis | 16.09.2025

## Answer Set-2
S.No | Term | Synonyms / Alternate Phrases | Answer | Section | Sub Section | Page Number
1 | Client Name | Employer / Project Owner / Principal / Contracting Authority | Bangalore Metro Rail Corporation Ltd. (BMRCL) | Section A | NIT | 6
2 | Client Name | Employer / Project Owner / Principal / Contracting Authority | Bangalore Metro Rail Corporation Ltd. (BMRCL) - Joint Venture of Government of Karnataka and Government of India | Section A | NIT | 6
3 | Funding Agency, if any | Financier / Sponsor / Donor Agency / Funding Authority | EIB (European Investment Bank) and AIIB (Asian Infrastructure Investment Bank) (Subject to loan approval) - part of the funding with GoI and GoK(equity Split) | Section A | NIT | 6
4 | Bidding System | Tendering Process / Bid Submission Format | Single stage – Two Envelope System (Technical & Financial separately) Envelope-1: Tender Security. (Details in NIT and ITT Clause 13) Envelope-2: Technical Proposal. (Details in ITT Clause 9.2) Envelope-3: Financial Proposal. (Details in ITT Clause 9.4) Envelope-4: Outer Envelope.
5 | Name of the Work | Project Title / Scope of Work / Work Description / Contract Name | Design & Construction of Underground Structures (Tunnels & Stations) from Shivajinagar (Excl.) to Tannery Road (Excl.), 2.884 km, including Cantonment and Pottery Town UG stations, Reach-6, Phase-2
6 | Project Location | Site Address / Worksite / Construction Site / Project Area | Bangalore, Karnataka, India; Reach-6 Metro - Shivajinagar to Tannery Road
7 | Completion Period | Duration / Timeframe / Contract Period / Execution Time | 42 Months (1260 days) from date of signing Contract Agreement | Section A | NIT | 6
8 | Estimated Cost | Project Value / Budget Estimate / Approximate Cost / Cost Projection | ₹ 1105.42 Crores | Section A | NIT | 6
9 | Cost of Tender Document | Tender Fee / Bid Document Charges / Application Fee / Document Cost | ₹ 56,000 (inclusive of GST) | Section A | NIT | 6
10 | Earnest Money Deposit (EMD) | Bid Security / Tender Deposit / Performance Guarantee (initial) | ₹ 11.06 Crores (in form of BG/Pay Order/DD, valid for 240 days from date of bid submission) | Section A | NIT | 6
11 | Important Dates |  | - Issue: 26.06.2018 | Section A | NIT | 6
|  |  | - Sale up to: 07.08.2018 | Section A | NIT | 6
|  |  | Pre-bid meeting: 16.07.2018 at 11.00 hrs | Section A | NIT | 6
|  |  | Last date of queries: 17.07.2018 at 17.30 hrs | Section A | NIT | 6
|  |  | - Submission: 07.09.2018 (11:00–15:00 Hrs) | Section A | NIT | 6
|  |  | - Opening: 07.09.2018 (15:30 Hrs) | Section A | NIT | 6
12 | Website |  | www.bmrc.co.in
13 | Index |  | Index of tender documents | Section A | NIT | 7
14 | Procedures to tenderers for online purchase of tender documents |  | Visit web site: www.bmrc.co.in ii. Register online. (one-time process) iii. Make payment through Gate Way as available in the website. iv. Down load, complete tender document. v. Frequently check website and also registered mail for any Addendum/Corrigendum/Answered Pre bid queries. | Section A | NIT | 7
15 | Procedure for tenderers opting for downloading of tender documents using Login pass word against DD. |  | Visit web site: www.bmrc.co.in ii. Enter login password obtained from BMRCL on submission of DD. iii. Down load, complete tender document. iv. Frequently check website and also registered mail for any Addendum/Corrigendum/Answered Pre bid queries. | Section A | NIT | 7
16 | Bid Validity | Proposal Validity / Offer Duration / Tender Validity Period | 180 days from date of submission | Section A | NIT | 8
17 | Tender Security |  | 240 days from date of submission C-12 , C-13 of ITT | Section A | NIT | 8
18 | Joint Venture? | Consortium / Partnership / JV Agreement / Strategic Alliance | Allowed; max 3 partners, with rules on % participation (Lead ≥ 50%, Others ≥ 25%)- Appendix 31 , Schedule 12 of SCC | Section B | ITT | 10
19 | Power of Attorney | Letter of Authorization / POA / Authority Letter / Legal Mandate | Required, both for signing the bid and for JV arrangements; foreign PoAs to be notarized and legalized | Section B | ITT | 11
20 | Grounds for bid rejection 2.7 of ITT | Disqualification Reasons / Non-compliance Issues / Rejection Criteria | - Late bid | Section B | ITT.2.7 | 11
- Non-submission/invalid EMD
- No separate sealed envelopes for Tech/Fin
- Not meeting eligibility/qualification
One institute One bid
- Conflict of interest/prohibited, fraudulent, or corrupt practices
False information, errors, insufficient documentation, modification attempts after deadline, etc. [Detailed in ITT 2.7, 13.2, 21, and EQC]
Clause 1.3 of ITT , 2.8 of ITT , sub cluse - 4.33 of GCC , Appendix 34
21 | Site Visit | Site Inspection / Pre-bid Visit / Field Visit / On-site Evaluation | Mandatory, at own cost/risk; was advised by employer for all bidders, given data is for guidance only. | Section B | ITT.4.0 | 13
22 | Geotechnical Investigation Reports | Soil Investigation Report / Geo Report / Subsurface Study / Soil Testing Report | Reference data provided; tenderers can carry out their own investigation for bid preparation | Section B Technical specification - Volume 2 - Section 2 - Outline design specification | ITT.4.2 | 13
23 | Land Availability | Site Access / Land Ownership / Plot Readiness / Site Handing-over | The notification for land acquisition has been issued and is in process. The joint measurement work is under process and the final notification is awaited. The Tender for demolition of buildings is invited and awarded. Casting yard land (near Peenya Depot ~23,261 sqm) provided for casting activities; more land, if required, must be arranged by contractor, Necessary permanent utility diversion to done by the employer thorugh the separate contract. | Section B GCC Clause 2.2 GCC Clause 8.4.1 GCC Clause 8.4.3 | ITT4.3&4.4 | 14
24 | Other land availability | Right of Way (RoW) / Utility Relocation Status / Encumbrance Clearance | No additional land acquisition support from employer beyond specified casting yard | Section B | ITT4.4 | 14
25 | Amendment to tender documents |  | During the tender period, the Employer may issue further instructions to Tenderers or any modifications to existing tender documents in the form of an addendum. | Section B GCC Clause 1.5 Sub Clause 18 - ITT | ITT.7 | 15
26 | Language of tender |  | All documents shall be in English Language. In case any accompanying printed literature is in other language, it shall be accompanied by English translation. The English version shall prevail in matters of interpretation. | Section B | ITT.8 | 16
27 | Technical bid submittals | Qualification Documents / Tech Proposal / Technical Documents | - Technical Proposal Vol-1, 2, 3 (duly signed, stamped) | Section B | ITT9.2.1 | 16
|  |  | - Annual & Financial Reports | Section B | ITT9.2.1 | 16
|  |  | - Memorandum & Article of Association | Section B | ITT9.2.1 | 16
|  |  | - Addenda/Corrigenda | Section B | ITT9.2.1 | 16
|  |  | Details of providers of guarantees and warranties under sub-clause 4.2 of GCC. | Section B GCC Clause 4.2 | ITT9.2.1 | 16
|  |  | - All eligibility/qualifying documents, power(s) of attorney, MoU/JVA if JV | Section B | ITT9.2.1 | 16
|  |  | - Approach & Methodology, Site Organization, Work Programme, Equipment, Key Personnel, Safety/Quality Plans, Statement of Deviations [see section 9.2, 9.2.1, 9.2.2, EQC] | Section B | ITT9.2.1 | 16
|  |  | Statements of deviations | Appendix 28
|  |  | Tender Price | Section B | ITT.10 | 18
28 | Financial/Cost bid submittals | Price Proposal / Commercial Bid / Cost Sheets / BOQ Submission | - Financial Proposal in separate sealed envelope | Section B | ITT.9.4.1 | 17
|  |  | - Summary of Price Bid | Section B | ITT.9.4.1 | 17
|  |  | - Form of Price Bid | Section B | ITT.9.4.1 | 17
|  |  | - Preamble | Section B | ITT.9.4.1 | 17
|  |  | - Schedule-C BOQ & Breakup of Payment | Section B | ITT.9.4.1 | 17
|  |  | - Appendix-35 (Pricing of Conditions/Deviations) | Section B | ITT.9.4.1 | 17
29 | CURRENCIES OF THE TENDER |  | Tender prices shall be quoted in Indian Rupees only | Section B | ITT.11 | 18
30 | List of Banks for Bank guarantee |  | An Indian Scheduled Bank (excluding Co-operative banks) or from a Schedule Foreign Bank as defined in Section 2 (e) of RBI Act 1934 read with Second Schedule | Section B | ITT.13.1 | 18
31 | Sealing and marking of the tenders |  | Envelop 4: outer envelop, envelop-01: tender security, envelop-02: technical proposal, envelop-03: financial proposal | Section B | ITT.17 | 20
32 | Address at which tenders to be submitted |  | General Manager/Contracts BMRCL, Third Floor, BMTC Complex, KH Road, Shantinagar, Bangalore-560 027, Karnataka, India | Section B | ITT.18.1 | 20
33 | Submission of tenders |  | Sealed tenders shall be submitted in person to the designated office. Tenders submitted through post will be rejected. | Section B | ITT.18.2 | 20
34 | Documents to be submitted within 30 days of contract award |  | Perfromance guarantee, Power of Attorney(s), Detailed Joint venture agreement. | Section B | ITT.30.2 | 24
35 | Perfromance guarantee in case of JV |  | Each member of the JV shall submit the performance guarantee in their name separately, proportion to their participation | Section B | ITT.31 | 24
36 | Contact person in BMRCL office |  | General Manager (Contracts) Telephone No. 080-22969300 and Fax No: 080-22969222, Email:- contracts@bmrc.co.in | Section B | ITT.34 | 24
37 | Eligibility Criteria | Prequalification Requirements / Qualification Norms / Bidder Criteria | - Work experience: Similar nature (TBM tunnel, min. 5m dia.), ≥3.92 km in last 10 years (JVs allowed conditions apply) | Section C | EQC | 27
|  |  | The number of Joint Venture Partners shall be restricted to maximum of THREE. | Section C | EQC.2.2 | 27
|  |  | Bid capacity should be greater than or equal to the cost of the current project. | Section C | EQC.3.2 | 27
|  |  | - DDC: Work for at least 2 UG metro stations & 1.0 km tunnel | Section C | EQC.3.2A | 27
|  |  | - Financial: Positive net worth last 2 FYs, EBIT positive 2 out of last 5 FYs, liquidity ≥₹221.08 Cr, annual turnover min. ₹947.50 Cr for 2 years out of last 5, bid capacity ≥₹1105.42 Cr (See detailed EQC Sec-C, pages 3-9) | Section C | EQC.3.2C | 31
38 | Eligibility of JV partners |  | Tenderer (each member in case of JV) should have the experience as a contractor in civil engineering construction works for last seven years. | Section C | EQC.2.1 | 27
39 | Office of design consultant |  | Detailed Design Consultant of the successful Tenderer must establish its office at Bangalore | Section C | EQC.2.7 | 27
40 | Appointment of Key Personnel |  | The Tenderers must deploy the Key Personnel for the work as indicated in Appendix -23 of FTT | Section C | EQC.3.3 | 32
41 | TBM to be deployed |  | The Tenderers are to note that deployment of a minimum of TWO TBMs is mandatory | Section C | EQC.3.4 | 32
42 | Plant & machineries |  | Plant & machineries as indicated in Appendix-16 are only indicative and should be considered in the tender submittal along with any other additional plant & machineries. | Section C | EQC.3.4 | 32
43 | Documents to be submitted | Credentials to be submitted/Submittals/Contractual deliverables | - All as per ITT 9.2/9.4 and EQC 1.3/1.5/2.3/3.4 etc.
- Forms of Tender, Appendices 8–17, 28, 31–35, technical/financial forms, DDC warranty, Key personnel CVs, plant/machinery list, etc.
44 | contract prices and payment |  | copies of acknowledgements evidencing filing of returns every year | Section E | GCC 11.2 | 137
45 |  |  | All Variations shall be recorded in a written instruction from the Engineer | Section E | GCC 12.1 | 138
46 |  |  | value engineering proposals for modifying the Employer’s Requirements | Section E | GCC 12.2.1 | 138
47 |  |  | a. a general description of the original Contract requirements for the Works and the proposed changes b. any detail of all the proposed modifications to the drawings and specifications c. any detail of all Work and goods affected by the value engineering proposal d. a detailed estimate of the construction cost based on the original Contract requirements and based on the proposed changes e. any resultant time extensions or reductions for the Contract f. statement to the extent of minimum saving expected. The Contractor’s cost of preparing value engineering proposal shall be excluded in determining the estimated net savings in construction costs. | Section E | GCC 12.2.2 | 138
48 |  |  | a description of the proposed work to be performed and a programme for its execution, the Contractor’s proposal for any necessary modifications to the programme according to Sub-Clause 4.13, and the Contractor's proposal for adjustment to the Contract Price, Time for Completion and/or modifications to the Contract. | Section E | GCC 12.3 | 139
49 |  |  | The contractor shall submit copies of PI policies | Section E | GCC 15.6 | 146
50 |  |  | When each premium is paid, contractor should submit a reciept to client and notify the engineer | Section E | GCC 15.7 | 147
51 |  |  | Within 30 days of the date of Letter of acceptance, and thereafter at the end of each calendar month, the Contractor shall submit to the Engineer his Three Month Rolling Programme for each agreed major section of Works in the Contract | Section F | SCC 2 | 158
52 |  |  | Within 8 weeks of receipt of letter of acceptance, the Contractor shall submit a detailed and comprehensive contract-specific Site Safety Plan based on the Employer’s Safety, Health and Environmental Manual (SHE Manual) | Section F | SCC 3 | 158
53 |  |  | The Contractor shall submit to the Engineer all Design Data, together with the relevant Design Certificates certified by the Contractor | Section F | SCC 5 | 160
54 |  |  | The contractor shall demonstrate the advance payment has been used by submitting copies of invoices and other documents to the employer | Section F | SCC 7 | 164
55 |  |  | Indamnity bond needs to be submitted along with Bank guarantee in favour of the employer | Section F | SCC 8 | 165
56 |  |  | The contractor shall submit certified copies of vouchers showing quantity of cement and steel brought at site for Engineer’s record. | Section F | SCC 11 | 167
57 |  |  | contractor is required to submit Price variation bills quarterly. | Section F | SCC 11 | 167
58 |  |  | The copies of the supporting vouchers of the disbursement made by the Contractor should also be attached with the IPC. | Section F | SCC 11 | 167
59 |  |  | The Bank Guarantees to be submitted by contractors. The Bank Guarantees of subcontractors are not acceptable. | Section F | SCC 11.1 | 168
60 |  |  | In all cases where extra items of work are involved, for which there are no rates in the accepted Bill of Quantities, the Contractor shall give a notice to the Engineer, of at least 7 days before the need for their execution arises. | Section F | SCC 12.2.2 | 172
61 |  |  | Contract Agreement | Section G | Schedule 1 | 175
62 |  |  | Bank Guarantee for performane of contract (Sole contractor) | Section G | Schedule 2A | 179
63 |  |  | Bank Guarantee for performane of contract (Each member of JV) | Section G | Schedule 2B | 181
64 |  |  | Parent Company Undertaking | Section G | Schedule 3 | 184
65 |  |  | Parent Company Guarantee | Section G | Schedule 4 | 187
66 |  |  | Contractors Warranty | Section G | Schedule 5 | 189
67 |  |  | Sub-contractor/Vendor's Warranty | Section G | Schedule 6 | 192
68 |  |  | Bank Guarantee for payment of mobilization advance / Plant and machinery advance | Section G | Schedule 7 | 195
69 |  |  | Bank Guarantee for Payment of Retention money | Section G | Schedule 8 | 197
70 |  |  | Bank guarantee for safe custody of materials supplied by employer to the contractor | Section G | Schedule 9 | 200
71 |  |  | Special advance bank guarantee | Section G | Schedule 10 | 202
72 |  |  | Draft format for joint venture / Consortium agreement | Section G | Schedule 11 | 205
73 | Tender Index |  | The Tenderer shall include with his Tender an index which cross refers all of the Employer’s tender requirements |  |  | 77
74 | The Employer |  | If the Contractor or any partner of the Contractor or Director of the Contractor’s company is closely related to any of the Officers of the Employer or the Engineer, or alternatively, if any close relative of an officer of the Employer or the Engineer has financial interest / stake in the Contractor’s firm, the same shall be disclosed by the Contractor at the time of filing his tender. | Section E | GCC 4.21 | 118

## Answer Set-2 (2)
S.No | Term | Answer- Manual Findings | Section | Sub Section | Page Number
1 | Client Name | Bangalore Metro Rail Corporation Ltd. (BMRCL) | Section A | NIT | 6
2 | Client Name | Bangalore Metro Rail Corporation Ltd. (BMRCL) - Joint Venture of Government of Karnataka and Government of India | Section A | NIT | 6
3 | Funding Agency, if any | EIB (European Investment Bank) and AIIB (Asian Infrastructure Investment Bank) (Subject to loan approval) - part of the funding with GoI and GoK(equity Split) | Section A | NIT | 6
4 | Bidding System | Single stage – Two Envelope System (Technical & Financial separately) Envelope-1: Tender Security. (Details in NIT and ITT Clause 13) Envelope-2: Technical Proposal. (Details in ITT Clause 9.2) Envelope-3: Financial Proposal. (Details in ITT Clause 9.4) Envelope-4: Outer Envelope.
5 | Name of the Work | Design & Construction of Underground Structures (Tunnels & Stations) from Shivajinagar (Excl.) to Tannery Road (Excl.), 2.884 km, including Cantonment and Pottery Town UG stations, Reach-6, Phase-2
6 | Project Location | Bangalore, Karnataka, India; Reach-6 Metro - Shivajinagar to Tannery Road
7 | Completion Period | 42 Months (1260 days) from date of signing Contract Agreement | Section A | NIT | 6
8 | Estimated Cost | ₹ 1105.42 Crores | Section A | NIT | 6
9 | Cost of Tender Document | ₹ 56,000 (inclusive of GST) | Section A | NIT | 6
10 | Earnest Money Deposit (EMD) | ₹ 11.06 Crores (in form of BG/Pay Order/DD, valid for 240 days from date of bid submission) | Section A | NIT | 6
11 | Important Dates | - Issue: 26.06.2018 | Section A | NIT | 6
|  | - Sale up to: 07.08.2018 | Section A | NIT | 6
|  | Pre-bid meeting: 16.07.2018 at 11.00 hrs | Section A | NIT | 6
|  | Last date of queries: 17.07.2018 at 17.30 hrs | Section A | NIT | 6
|  | - Submission: 07.09.2018 (11:00–15:00 Hrs) | Section A | NIT | 6
|  | - Opening: 07.09.2018 (15:30 Hrs) | Section A | NIT | 6
12 | Website | www.bmrc.co.in
13 | Index | Index of tender documents | Section A | NIT | 7
14 | Procedures to tenderers for online purchase of tender documents | Visit web site: www.bmrc.co.in ii. Register online. (one-time process) iii. Make payment through Gate Way as available in the website. iv. Down load, complete tender document. v. Frequently check website and also registered mail for any Addendum/Corrigendum/Answered Pre bid queries. | Section A | NIT | 7
15 | Procedure for tenderers opting for downloading of tender documents using Login pass word against DD. | Visit web site: www.bmrc.co.in ii. Enter login password obtained from BMRCL on submission of DD. iii. Down load, complete tender document. iv. Frequently check website and also registered mail for any Addendum/Corrigendum/Answered Pre bid queries. | Section A | NIT | 7
16 | Bid Validity | 180 days from date of submission | Section A | NIT | 8
17 | Tender Security | 240 days from date of submission C-12 , C-13 of ITT | Section A | NIT | 8
18 | Joint Venture? | Allowed; max 3 partners, with rules on % participation (Lead ≥ 50%, Others ≥ 25%)- Appendix 31 , Schedule 12 of SCC | Section B | ITT | 10
19 | Power of Attorney | Required, both for signing the bid and for JV arrangements; foreign PoAs to be notarized and legalized | Section B | ITT | 11
20 | Grounds for bid rejection 2.7 of ITT | - Late bid | Section B | ITT.2.7 | 11
- Non-submission/invalid EMD
- No separate sealed envelopes for Tech/Fin
- Not meeting eligibility/qualification
One institute One bid
- Conflict of interest/prohibited, fraudulent, or corrupt practices
False information, errors, insufficient documentation, modification attempts after deadline, etc. [Detailed in ITT 2.7, 13.2, 21, and EQC]
Clause 1.3 of ITT , 2.8 of ITT , sub cluse - 4.33 of GCC , Appendix 34
21 | Site Visit | Mandatory, at own cost/risk; was advised by employer for all bidders, given data is for guidance only. | Section B | ITT.4.0 | 13
22 | Geotechnical Investigation Reports | Reference data provided; tenderers can carry out their own investigation for bid preparation | Section B Technical specification - Volume 2 - Section 2 - Outline design specification | ITT.4.2 | 13
23 | Land Availability | The notification for land acquisition has been issued and is in process. The joint measurement work is under process and the final notification is awaited. The Tender for demolition of buildings is invited and awarded. Casting yard land (near Peenya Depot ~23,261 sqm) provided for casting activities; more land, if required, must be arranged by contractor, Necessary permanent utility diversion to done by the employer thorugh the separate contract. | Section B GCC Clause 2.2 GCC Clause 8.4.1 GCC Clause 8.4.3 | ITT4.3&4.4 | 14
24 | Other land availability | No additional land acquisition support from employer beyond specified casting yard | Section B | ITT4.4 | 14
25 | Amendment to tender documents | During the tender period, the Employer may issue further instructions to Tenderers or any modifications to existing tender documents in the form of an addendum. | Section B GCC Clause 1.5 Sub Clause 18 - ITT | ITT.7 | 15
26 | Language of tender | All documents shall be in English Language. In case any accompanying printed literature is in other language, it shall be accompanied by English translation. The English version shall prevail in matters of interpretation. | Section B | ITT.8 | 16
27 | Technical bid submittals | - Technical Proposal Vol-1, 2, 3 (duly signed, stamped) | Section B | ITT9.2.1 | 16
|  | - Annual & Financial Reports | Section B | ITT9.2.1 | 16
|  | - Memorandum & Article of Association | Section B | ITT9.2.1 | 16
|  | - Addenda/Corrigenda | Section B | ITT9.2.1 | 16
|  | Details of providers of guarantees and warranties under sub-clause 4.2 of GCC. | Section B GCC Clause 4.2 | ITT9.2.1 | 16
|  | - All eligibility/qualifying documents, power(s) of attorney, MoU/JVA if JV | Section B | ITT9.2.1 | 16
|  | - Approach & Methodology, Site Organization, Work Programme, Equipment, Key Personnel, Safety/Quality Plans, Statement of Deviations [see section 9.2, 9.2.1, 9.2.2, EQC] | Section B | ITT9.2.1 | 16
|  | Statements of deviations | Appendix 28
|  | Tender Price | Section B | ITT.10 | 18
28 | Financial/Cost bid submittals | - Financial Proposal in separate sealed envelope | Section B | ITT.9.4.1 | 17
|  | - Summary of Price Bid | Section B | ITT.9.4.1 | 17
|  | - Form of Price Bid | Section B | ITT.9.4.1 | 17
|  | - Preamble | Section B | ITT.9.4.1 | 17
|  | - Schedule-C BOQ & Breakup of Payment | Section B | ITT.9.4.1 | 17
|  | - Appendix-35 (Pricing of Conditions/Deviations) | Section B | ITT.9.4.1 | 17
29 | CURRENCIES OF THE TENDER | Tender prices shall be quoted in Indian Rupees only | Section B | ITT.11 | 18
30 | List of Banks for Bank guarantee | An Indian Scheduled Bank (excluding Co-operative banks) or from a Schedule Foreign Bank as defined in Section 2 (e) of RBI Act 1934 read with Second Schedule | Section B | ITT.13.1 | 18
31 | Sealing and marking of the tenders | Envelop 4: outer envelop, envelop-01: tender security, envelop-02: technical proposal, envelop-03: financial proposal | Section B | ITT.17 | 20
32 | Address at which tenders to be submitted | General Manager/Contracts BMRCL, Third Floor, BMTC Complex, KH Road, Shantinagar, Bangalore-560 027, Karnataka, India | Section B | ITT.18.1 | 20
33 | Submission of tenders | Sealed tenders shall be submitted in person to the designated office. Tenders submitted through post will be rejected. | Section B | ITT.18.2 | 20
34 | Documents to be submitted within 30 days of contract award | Perfromance guarantee, Power of Attorney(s), Detailed Joint venture agreement. | Section B | ITT.30.2 | 24
35 | Perfromance guarantee in case of JV | Each member of the JV shall submit the performance guarantee in their name separately, proportion to their participation | Section B | ITT.31 | 24
36 | Contact person in BMRCL office | General Manager (Contracts) Telephone No. 080-22969300 and Fax No: 080-22969222, Email:- contracts@bmrc.co.in | Section B | ITT.34 | 24
37 | Eligibility Criteria | - Work experience: Similar nature (TBM tunnel, min. 5m dia.), ≥3.92 km in last 10 years (JVs allowed conditions apply) | Section C | EQC | 27
|  | The number of Joint Venture Partners shall be restricted to maximum of THREE. | Section C | EQC.2.2 | 27
|  | Bid capacity should be greater than or equal to the cost of the current project. | Section C | EQC.3.2 | 27
|  | - DDC: Work for at least 2 UG metro stations & 1.0 km tunnel | Section C | EQC.3.2A | 27
|  | - Financial: Positive net worth last 2 FYs, EBIT positive 2 out of last 5 FYs, liquidity ≥₹221.08 Cr, annual turnover min. ₹947.50 Cr for 2 years out of last 5, bid capacity ≥₹1105.42 Cr (See detailed EQC Sec-C, pages 3-9) | Section C | EQC.3.2C | 31
38 | Eligibility of JV partners | Tenderer (each member in case of JV) should have the experience as a contractor in civil engineering construction works for last seven years. | Section C | EQC.2.1 | 27
39 | Office of design consultant | Detailed Design Consultant of the successful Tenderer must establish its office at Bangalore | Section C | EQC.2.7 | 27
40 | Appointment of Key Personnel | The Tenderers must deploy the Key Personnel for the work as indicated in Appendix -23 of FTT | Section C | EQC.3.3 | 32
41 | TBM to be deployed | The Tenderers are to note that deployment of a minimum of TWO TBMs is mandatory | Section C | EQC.3.4 | 32
42 | Plant & machineries | Plant & machineries as indicated in Appendix-16 are only indicative and should be considered in the tender submittal along with any other additional plant & machineries. | Section C | EQC.3.4 | 32
43 | Documents to be submitted | - All as per ITT 9.2/9.4 and EQC 1.3/1.5/2.3/3.4 etc.
- Forms of Tender, Appendices 8–17, 28, 31–35, technical/financial forms, DDC warranty, Key personnel CVs, plant/machinery list, etc.
44 | contract prices and payment | copies of acknowledgements evidencing filing of returns every year | Section E | GCC 11.2 | 137
45 |  | All Variations shall be recorded in a written instruction from the Engineer | Section E | GCC 12.1 | 138
46 |  | value engineering proposals for modifying the Employer’s Requirements | Section E | GCC 12.2.1 | 138
47 |  | a. a general description of the original Contract requirements for the Works and the proposed changes b. any detail of all the proposed modifications to the drawings and specifications c. any detail of all Work and goods affected by the value engineering proposal d. a detailed estimate of the construction cost based on the original Contract requirements and based on the proposed changes e. any resultant time extensions or reductions for the Contract f. statement to the extent of minimum saving expected. The Contractor’s cost of preparing value engineering proposal shall be excluded in determining the estimated net savings in construction costs. | Section E | GCC 12.2.2 | 138
48 |  | a description of the proposed work to be performed and a programme for its execution, the Contractor’s proposal for any necessary modifications to the programme according to Sub-Clause 4.13, and the Contractor's proposal for adjustment to the Contract Price, Time for Completion and/or modifications to the Contract. | Section E | GCC 12.3 | 139
49 |  | The contractor shall submit copies of PI policies | Section E | GCC 15.6 | 146
50 |  | When each premium is paid, contractor should submit a reciept to client and notify the engineer | Section E | GCC 15.7 | 147
51 |  | Within 30 days of the date of Letter of acceptance, and thereafter at the end of each calendar month, the Contractor shall submit to the Engineer his Three Month Rolling Programme for each agreed major section of Works in the Contract | Section F | SCC 2 | 158
52 |  | Within 8 weeks of receipt of letter of acceptance, the Contractor shall submit a detailed and comprehensive contract-specific Site Safety Plan based on the Employer’s Safety, Health and Environmental Manual (SHE Manual) | Section F | SCC 3 | 158
53 |  | The Contractor shall submit to the Engineer all Design Data, together with the relevant Design Certificates certified by the Contractor | Section F | SCC 5 | 160
54 |  | The contractor shall demonstrate the advance payment has been used by submitting copies of invoices and other documents to the employer | Section F | SCC 7 | 164
55 |  | Indamnity bond needs to be submitted along with Bank guarantee in favour of the employer | Section F | SCC 8 | 165
56 |  | The contractor shall submit certified copies of vouchers showing quantity of cement and steel brought at site for Engineer’s record. | Section F | SCC 11 | 167
57 |  | contractor is required to submit Price variation bills quarterly. | Section F | SCC 11 | 167
58 |  | The copies of the supporting vouchers of the disbursement made by the Contractor should also be attached with the IPC. | Section F | SCC 11 | 167
59 |  | The Bank Guarantees to be submitted by contractors. The Bank Guarantees of subcontractors are not acceptable. | Section F | SCC 11.1 | 168
60 |  | In all cases where extra items of work are involved, for which there are no rates in the accepted Bill of Quantities, the Contractor shall give a notice to the Engineer, of at least 7 days before the need for their execution arises. | Section F | SCC 12.2.2 | 172
61 |  | Contract Agreement | Section G | Schedule 1 | 175
62 |  | Bank Guarantee for performane of contract (Sole contractor) | Section G | Schedule 2A | 179
63 |  | Bank Guarantee for performane of contract (Each member of JV) | Section G | Schedule 2B | 181
64 |  | Parent Company Undertaking | Section G | Schedule 3 | 184
65 |  | Parent Company Guarantee | Section G | Schedule 4 | 187
66 |  | Contractors Warranty | Section G | Schedule 5 | 189
67 |  | Sub-contractor/Vendor's Warranty | Section G | Schedule 6 | 192
68 |  | Bank Guarantee for payment of mobilization advance / Plant and machinery advance | Section G | Schedule 7 | 195
69 |  | Bank Guarantee for Payment of Retention money | Section G | Schedule 8 | 197
70 |  | Bank guarantee for safe custody of materials supplied by employer to the contractor | Section G | Schedule 9 | 200
71 |  | Special advance bank guarantee | Section G | Schedule 10 | 202
72 |  | Draft format for joint venture / Consortium agreement | Section G | Schedule 11 | 205
73 | Tender Index | The Tenderer shall include with his Tender an index which cross refers all of the Employer’s tender requirements |  |  | 77
74 | The Employer | If the Contractor or any partner of the Contractor or Director of the Contractor’s company is closely related to any of the Officers of the Employer or the Engineer, or alternatively, if any close relative of an officer of the Employer or the Engineer has financial interest / stake in the Contractor’s firm, the same shall be disclosed by the Contractor at the time of filing his tender. | Section E | GCC 4.21 | 118

## Output Comparison
S.No |  | Manual | Gemini | Perplexity
1 | Client Name
2 | Funding Agency, if any
3 | Bidding System
4 | Name of the Work
5 | Project Location
6 | Completion Period
7 | Estimated Cost
8 | Cost of Tender Document
9 | Earnest Money Deposit (EMD) / Tender Security
10 | Important Dates (Sale/Download of Tender Documents)
11 | Important Dates (Pre-bid meeting)
12 | Important Dates (Date & time for submission of Tenders)
13 | Pre-bid meeting?
14 | Joint Venture?
15 | Power of Attorney
16 | Site Visit?
17 | Geotechnical Investigation Reports
18 | Land Availability (for work/labor camp)
19 | Other land availability
20 | Technical bid submittals
21 | Financial/Cost bid submittals
22 | Bid Validity
23 | Grounds for bid rejection

## Gemini Output
S. No. | Objective File Requirement | Tender Document Detail | Source(s)
1 | Client Name | Bangalore Metro Rail Corporation Limited (BMRCL) (A Joint Venture of GOK & GOI)
2 | Funding Agency, if any | BMRCL is applying for a Loan from bilateral/multilateral funding agency/agencies (EIB and AIIB) towards part cost of the Project. The remaining portion shall be financed through equity participation by the Government of India and Government of Karnataka.
3 | Bidding System | Single stage Two Envelope System
4 | Name of the Work | "Design & Construction of Underground structures (Tunnels & Stations) of length 2.884 Km (approx.) from Shivajinagar Station (excluding) to Tannery Road Station (excluding) (Chainage 13938.328 m to 16822.521 m) including allied works and 2 Nos of UG Metro Stations viz Cantonment and Pottery Town in Reach-6 line of Bangalore Metro Rail Project, Phase-2."
5 | Project Location | Bangalore (Bengaluru), Karnataka, India
6 | Completion Period | 42 Months
7 | Estimated Cost | INR 1105.42 Crores
8 | Cost of Tender Document | INR 56,000 (Rupees Fifty Six Thousand Only) (inclusive of GST)
9 | Earnest Money Deposit (EMD) / Tender Security | INR 11.06 Crores
10 | Important Dates (Sale/Download of Tender Documents) | From 26.06.2018 to 07.08.2018 (until midnight of 07.08.2018 for online download)
11 | Important Dates (Pre-bid meeting) | 16/07/2018 at 11.00 hrs
12 | Important Dates (Date & time for submission of Tenders) | 07−09−2018 (from 11.00 Hrs to 15.00 Hrs)
13 | Pre-bid meeting? | Yes, scheduled for 16/07/2018 at 11.00 hrs. Attendance is not a cause for disqualification.
14 | Joint Venture? | Yes, JV is permitted. The number of members shall be restricted to maximum THREE. Lead member must have at least 50% participation, others a minimum of 25% individually.
15 | Power of Attorney | Required for the signatory/ies to commit the Tenderer or each JV member. Formats are provided in Appendix-29 and Appendix-30.
16 | Site Visit? | Yes, advised. The Tenderer is advised to visit and examine the Site of Works and its surroundings at his/their responsibility, risk and cost.
17 | Geotechnical Investigation Reports | For reference only. Tenderer is expected to satisfy himself with data furnished and if required, carry out investigations independently at his own cost.
18 | Land Availability (for work/labor camp) | BMRCL has 23261 Sqm of land near Peenya Depot for casting related works and any other works, but not for setting up of labour camp. The land will be given free of cost for the original contract period.
19 | Other land availability | If the contractor needs further area(s) for his activities, then he has to arrange for it at his own cost. No additional land will be acquired by BMRCL for this purpose.
20 | Technical bid submittals | Must include Technical Proposal (Volume-1, 2, 3), Annual Report/Financial Report, MoA/AoA, Addendum/Corrigendum, supporting documents for EQC, Details of providers of guarantees/warranties, Conceptual Design notes/calculations, Work Programme, Outline Quality, Safety, Health & Environmental Plan, and details of deviations (Appendix-28).
21 | Financial/Cost bid submittals | Must be in a separate sealed envelope (Envelope-3) and comprise: Summary of Price bid, Form of Price bid, Preamble, Outline Description/Bill of Quantities, and Appendix 35 (Pricing of Unqualified withdrawal of Conditions, Qualifications, Deviations, etc.).
22 | Bid Validity | Tenders shall be valid for a period of 180 days from the date of submission of Tenders.
23 | Grounds for bid rejection | Failure to include Tender Security. Inadequate Tender Security (wrong bank/validity/amount/not payable in Bangalore). Not substantially responsive to requirements/material deviation. Conflict of interest. Failure to accept correction of arithmetical errors.

## Perplexity
Aspect | Details
Client Name | Bangalore Metro Rail Corporation Ltd. (BMRCL)
Project Name | Design & Construction of Underground structures (Tunnels & Stations) of length 2.884 Km (approx.), Shivajinagar Station (excluding) to Tannery Road Station (excluding), including allied works; 2 UG stations: Cantonment & Pottery Town, Reach-6, Phase-2
Funding Agency | Government of India, Government of Karnataka, EIB & AIIB Loans (bilateral/multilateral funding)
Tender Notification | BMRCLPhase-2Reach-6UGTNLSTN R6-CC-02-RT03 201838 (Dated 26-06-2018)
Location | Bangalore City, Karnataka
Scope of Work | Design & construction of underground tunnels & stations (Cantonment & Pottery Town) total length: 2.884 Km, associated civil & allied works
Completion Period | 42 Months
Estimated Cost | INR 1105.42 Crores
Cost of Tender Document | INR 56,000 (Incl. GST)
Tender Security/Earnest Money Deposit (EMD) | INR 11.06 Crores
Sale of Tender Documents | 26-06-2018 to 07-08-2018
Pre-bid Meeting | 16-07-2018 at 11:00 hrs
Submission Deadline | 07-09-2018 (11:00–15:00 hrs IST)
Opening of Tender | 07-09-2018 at 15:30 hrs IST
Bid Validity | 180 days from submission date
Tender Security Validity | 240 days from submission
Bidding System | Single stage, two envelope system
Eligible Bidders | Qualified, reputed and experienced contractors/JVs with relevant experience in similar projects in last 10 years
Key Qualification Criteria | Annual Turnover: Minimum INR 473.75 Crores in at least 2 of last 5 years, aggregate INR 947.50 Crores. Experience in relevant underground metro works, positive net worth for last 2 years, profit before interest & tax in at least 2 years. Financial info certified by CA
Site Visit & Data | Mandatory site visit. Land & geotechnical data provided only for reference. Additional investigation at contractor's cost.
JV/Consortium | Allowed, max 3 members, lead member to hold at least 50% share.
Documents Required | Technical proposal (design comprehension, work scheduling, resource deployment, quality & safety plans), financial bid, eligibility & qualification proofs (CA certificate, client work certificates, power of attorney, JV MoU if applicable)
Award Criteria | Substantively responsive technical & financial bid with lowest evaluated reasonable price

## Documents to be submitted
Form of Tender
Sl. No. | Requirement | Submission Requirement | Page No
1 | Pro-Forma Letter of Application (Sole Tenderer) | Appendix-1 | 3
2 | Pro-Forma Letter of Declaration and Undertaking (Sole Tenderer) | Appendix-2 | 4
3 | Pro-Forma Letter of Application (Lead partner in case of JV) | Appendix-3 | 6
4 | Pro-Forma Letter of Declaration and Undertaking (Lead partner in case of JV) | Appendix-4 | 8
5 | Pro-Forma Letter of Application (Each partner other than Lead partner in case of JV) | Appendix-5 | 10
6 | Pro-Forma Letter of Declaration and Undertaking (Each partner other than Lead partner in case of JV) | Appendix-6 | 12
7 | Tenderer’s Information | Appendix-7 | 14
8 | Work of similar nature completed in the last 10 years. Submitted separately for each completed qualifying work. | Appendix-8 | 15
9 | Summary of the Information provided in Appendix-8 | Appendix-9 | 16
10 | Qualification Details of DDC | Appendix-9A | 17
11 | Litigation History | Appendix-9B | 18
12 | Updated Annual Turnover. | Appendix-10 | 19
13 | Works in Hand | Appendix-11 | 20
14 | Financial information certified by Chartered Accountant | Appendix-12 | 21
15 | Annual Turnover in case of JV | Appendix-13 | 22
16 | Net worth in case of JV | Appendix-14 | 23
17 | Profitability in case of JV | Appendix-15 | 24
18 | Plant and Machinery | Appendix-16 | 25
19 | Contract Data | Appendix-17 | 26
20 | Key Dates, Penalties, LD and Incentive clause, | Appendix-18 | 27
21 | Outline Quality Plan | Appendix-19 | 31
22 | Outline Safety Plan | Appendix-20 | 32
23 | Outline Environmental Plan | Appendix-21 | 33
24 | Tenderer's Technical Proposals | Appendix-22 | 34
25 | Minimum Qualification and Experience Required For Key Personnel for the work | Appendix-23 | 35
26 | Format of curriculum vitae (cv) for proposed key professional staff | Appendix-24 | 38
27 | Details of other personnel to be deployed to be given by successful bidder | Appendix-25 | 40
28 | Details of the personnel to be deployed by DDC of the successful bidder | Appendix-25A | 41
29 | Deleted | Appendix-26 | 42
30 | Tender Index | Appendix-27 | 43
31 | Statement of Deviation including Undertaking | Appendix-28 | 44
32 | Format For Power of Attorney For Signing of The Tender Documents by Tenderer(in case of Group by each member) | Appendix-29 | 47
33 | Format For Power of Attorney to Lead member (To be executed by the JV Members other than Lead partner) | Appendix-30 | 48
34 | Format for Memorandum of understanding for Joint venture participation | Appendix-31 | 50
35 | Form of Bank Guarantee for Tender Security | Appendix-32 | 53
36 | Form of Bankers Certificate | Appendix-33 | 55
37 | Covenant of Integrity | Appendix-34 | 56