## Questions
S.No | Analysing a Tender Document & Identifying Key Aspects in a Tender Document
1 | Client Name
2 | Funding Agency, if any
3 | Bidding System
4 | Name of the Work
5 | Project Location
6 | Completion Period
7 | Estimated Cost
8 | Cost of Tender Document
9 | Earnest Money Deposit (EMD)
10 | Important Dates
11 | Pre-bid meeting?
12 | Joint Venture?
13 | Power of Attorney
14 | Site Visit?
15 | Geotechnical Investigation Reports
16 | Land Availability
17 | Other land availability
18 | Technical bid submittals
19 | Financial/Cost bid submittals
20 | Bid Validity
21 | Grounds for bid rejection
22 | Eligibility Criteria
23 | Documents to be submitted

## Answers
S.No | Question | Answer | Good to Go??
1 | Client Name | Bangalore Metro Rail Corporation Ltd. (BMRCL) | ok
2 | Funding Agency, if any | EIB (European Investment Bank) and AIIB (Asian Infrastructure Investment Bank) (Subject to loan approval) - part of the funding with GoI and GoK(equity Split) | ok
3 | Bidding System | Single stage – Two Envelope System (Technical & Financial separately) Envelope-1: Tender Security. (Details in NIT and ITT Clause 13) Envelope-2: Technical Proposal. (Details in ITT Clause 9.2) Envelope-3: Financial Proposal. (Details in ITT Clause 9.4) Envelope-4: Outer Envelope. | ok
4 | Name of the Work | Design & Construction of Underground Structures (Tunnels & Stations) from Shivajinagar (Excl.) to Tannery Road (Excl.), 2.884 km, including Cantonment and Pottery Town UG stations, Reach-6, Phase-2 | ok
5 | Project Location | Bangalore, Karnataka, India; Reach-6 Metro - Shivajinagar to Tannery Road | ok
6 | Completion Period | 42 Months (1260 days) from date of signing Contract Agreement | ok
7 | Estimated Cost | ₹ 1105.42 Crores | ok
8 | Cost of Tender Document | ₹ 56,000 (inclusive of GST) | ok
9 | Earnest Money Deposit (EMD) | ₹ 11.06 Crores (in form of BG/Pay Order/DD, valid for 240 days from date of bid submission) | ok
10 | Important Dates | - Issue: 26.06.2018
- Sale up to: 07.08.2018
- Pre-bid meeting: 16.07.2018
- Last date of queries: 17.07.2018
- Submission: 07.09.2018 (11:00–15:00 Hrs)
- Opening: 07.09.2018 (15:30 Hrs)
11 | Pre-bid meeting? | Yes; 16/07/2018 at 11:00 am
12 | Joint Venture? | Allowed; max 3 partners, with rules on % participation (Lead ≥ 50%, Others ≥ 25%)
13 | Power of Attorney | Required, both for signing the bid and for JV arrangements; foreign PoAs to be notarized and legalized
14 | Site Visit? | Mandatory, at own cost/risk; was advised by employer for all bidders, given data is for guidance only.
15 | Geotechnical Investigation Reports | Reference data provided; tenderers can carry out their own investigation for bid preparation
16 | Land Availability | The notification for land acquisition has been issued and is in process. The joint measurement work is under process and the final notification is awaited. The Tender for demolition of buildings is invited and awarded. Casting yard land (near Peenya Depot ~23,261 sqm) provided for casting activities; more land, if required, must be arranged by contractor, Necessary permanent utility diversion to done by the employer thorugh the separate contract.
17 | Other land availability | No additional land acquisition support from employer beyond specified casting yard
18 | Technical bid submittals | - Technical Proposal Vol-1, 2, 3 (duly signed, stamped)
- Annual & Financial Reports
- Memorandum & Article of Association
- Addenda/Corrigenda
- All eligibility/qualifying documents, power(s) of attorney, MoU/JVA if JV
- Approach & Methodology, Site Organization, Work Programme, Equipment, Key Personnel, Safety/Quality Plans, Statement of Deviations [see section 9.2, 9.2.1, 9.2.2, EQC]
19 | Financial/Cost bid submittals | - Financial Proposal in separate sealed envelope
- Summary of Price Bid
- Form of Price Bid
- Preamble
- Schedule-C BOQ & Breakup of Payment
- Appendix-35 (Pricing of Conditions/Deviations)
20 | Bid Validity | 180 days from date of submission
21 | Grounds for bid rejection | - Late bid
- Non-submission/invalid EMD
- No separate sealed envelopes for Tech/Fin
- Not meeting eligibility/qualification
One institute One bid
- Conflict of interest/prohibited, fraudulent, or corrupt practices
- False information, errors, insufficient documentation, modification attempts after deadline, etc. [Detailed in ITT 2.7, 13.2, 21, and EQC]
22 | Eligibility Criteria | - Work experience: Similar nature (TBM tunnel, min. 5m dia.), ≥3.92 km in last 10 years (JVs allowed conditions apply)
Bid capacity should be greater than or equal to the cost of the current project.
- DDC: Work for at least 2 UG metro stations & 1.0 km tunnel
- Financial: Positive net worth last 2 FYs, EBIT positive 2 out of last 5 FYs, liquidity ≥₹221.08 Cr, annual turnover min. ₹947.50 Cr for 2 years out of last 5, bid capacity ≥₹1105.42 Cr (See detailed EQC Sec-C, pages 3-9)
23 | Documents to be submitted | - All as per ITT 9.2/9.4 and EQC 1.3/1.5/2.3/3.4 etc.
- Forms of Tender, Appendices 8–17, 28, 31–35, technical/financial forms, DDC warranty, Key personnel CVs, plant/machinery list, etc.